## Tabelle1
Tasks | Oktober |  |  |  |  | November |  |  |  |  | December | [5 empty] | January |  |  |  |  | February |  |  |  |  | March
Week -- Start -- End | 1 -- 7 | 8 -- 14 | 15 -- 21 | 22 -- 28 | 29 -- 4 |  | 5 -- 11 | 12 -- 18 | 19 -- 25 | 26 -- 2 |  | 3 -- 9 | 10 -- 16 | 17 -- 23 | 24 -- 30 | 31 -- 6 |  | 7 -- 13 | 14 -- 20 | 21 -- 27 | 28 -- 3 |  | 4 -- 10 | 11 -- 17 | 18 -- 24 | 25 -- 2 |  | 3 -- 9 | 10 -- 16 | 17 -- 23 | 24 -- 30 | 31
1. Preparations
(Optional) Reading on Trojans and DNNs
1.1 Present State of the Art
1.2 Define Threat Model
1.3 Find Datasets and Models to Evaluate
2. Attack Implementation
2.1 Read up on at Relevant Libraries and Ressources
2.2 Implement Networks for Attack
2.3 Implement Trigger Detector
2.4 Implement Malicious Behavior
3. Implement Defenses
4. Evaluation
4.1 Evaluate without Trojan
4.2 Evaluate with Trojan
4.3 Evaluate with Trojan and Defense
5. Thesis Writing